- Classify the project as an EIS and receive FHWA concurrence

- Letter of Initiation (LOI) to FHWA

  - Primary projects – OLE Director signs

  - Local systems projects – local sponsor signs

- Publish the Notice of Intent (NOI) in the Federal Register (may be sent to FHWA at the same time as LOI)

  - DOT drafts the NOI and sends an electronic copy to FHWA

  - FHWA forwards the NOI to the Federal Register

- Develop and sign the Joint Lead Agency MOU

  - For local systems projects only

  - Joint Lead Agencies = DOT, FHWA, Local Sponsor

  - 3 copies signed by all joint lead agencies.  Each joint lead agency gets one original signed copy.

- Develop Coordination Plan

  - For local systems projects, all joint lead agencies provide input in developing the plan

  - For primary projects, DOT develops the plan for FHWA concurrence

  - Lead agencies must concur on the plan, by email or meeting, before the plan is distributed to participating-cooperating (P&C) agencies

  - The plan will evolve during the NEPA process.  It will require periodic review and updates

- Identify and invite P&C agencies

  - Invitation letters (participating agency; cooperating agency) are sent to agencies.  FHWA (and DOT if local systems project) is copied only.  All carbon copies are sent to the NEPA document manager to distribute to DOT and FHWA.

-  For primary projects, letter signed by DOT

-  For local systems projects, letter signed by local sponsor

  - Ensure letter requests agency input on resources in the project area

  - For local systems projects, OLE, NEPA reviews the letter and attachments (map, project description, and coordination plan) before mailing

  - Tribal Notification letter/form and attachments sent to tribes

      - Get current list of tribal contacts and addresses from Cultural Resources Section

  - Consultant provides one copy each of P&C signed letters and list of recipients to OLE NEPA for administrative record

- Determine methodologies.  OLE NEPA meets with local sponsor/consultant to determine methodologies.  See OLE Manual, Part III, Ch. 17-41.

- Project Management Team (PMT) meeting to determine preliminary purpose and need (P&N), basic build/no build alternatives, and type of scoping to be performed.

  - For local systems projects, PMT is FHWA, local sponsor/ consultant, OLE NEPA, and other DOT representatives, as determined by District Local Systems Engineer

  - For primary projects, PMT membership typically includes representatives of the District; Offices of Design, Bridges & Structures, Right-of-Way, and OLE; FHWA; and other internal and external resources, as needed.

  - For primary projects, OLE NEPA gets update from consultant on status of NEPA.  OLE NEPA presents status update at PMT meeting.

  - Develop information, including methodologies, for scoping packet  and presentation at scoping meeting

  - Determine who will participate in the scoping process either at a scoping meeting or by mail

  - District sends meeting minutes to all PMT members.  OLE NEPA forwards minutes to the project advisory team (PAT)

- Conduct agency scoping to receive input on methodologies, P&N, basic build/no build alternatives, and to hear resource agency concerns

  - Send scoping packet/meeting invitation

      - If scoping meeting, send invitation and packet 30 days prior to meeting

      - If scoping packet only, allow 30 days for agencies to respond

      - Document meeting with good minutes and circulate to all P&C agencies for comment

- Begin environmental studies

  - Potential studies include:

      - wetland impacts

      - T&E species

      - noise impacts

      - regulated materials

      - cumulative impacts

      - 4(f) – identify potential 4(f) properties and complete Step 1 of decision process

      - historic and archaeological impacts

      - land use impacts

      - farmland impacts

      - social impacts, including EJ

      - relocation impacts

      - economic impacts

      - joint development

      - considerations relating to pedestrians and bicyclists

      - air quality impacts

      - water quality impacts

      - permits

      - water body modification and wildlife impacts

      - floodplain impacts

      - relationship of local short-term uses vs. long-term productivity

      - irreversible and irretrievable commitment of resources

- PMT meeting to refine preliminary P&N and build/no build alternatives and to prepare for the public information meeting (PIM)

  - Refine preliminary P&N and build/no build alternatives based on input from agency scoping and responses to participating/cooperating agency invitations

  - PIM roles determined

  - District sends meeting minutes to all PMT members.  OLE NEPA forwards minutes to PAT

- PIM for public input on P&N and build/no build alternatives

  - Work with OLE Hearing Section for primary projects

  - DOT NEPA reviews information prior to PIM

- Screen for engineering, environmental, and fiscal constraints (on-going)

  - Review early results of environmental studies and resource evaluations (Tech Memos)

- Develop build alternatives

- PMT meeting to determine build alternatives and to prepare for PIM

  - Determine build alternatives based on input from PIM, early results or resource evaluations, and screening for engineering, environmental, and fiscal constraints

  - PIM roles determined

  - District sends meeting minutes to all PMT members.  OLE NEPA forwards minutes to PAT

- PIM for public input on build alternatives

- NEPA/404 merge concurrence points 1 (P&N) & 2 (alternatives to be analyzed)

  - Purpose and Need and alternatives to be analyzed are reviewed by FHWA for their concurrence prior to meeting.

  - Required for primary projects

  - Not required for local systems projects, but strongly encouraged

  - Wetlands Section schedules meeting and prepares information packet to be sent out 30 days prior to meeting (primary projects)

  - OLE NEPA presents P&N (may use Power Point), Location engineer present alternatives (primary projects)

- Screen for engineering, environmental, and fiscal constraints (task completed by Location/consultant/PMT members)

- Refine build alternatives

  - Complete steps 2 through 5 of 4(f) decision process

- Receive tech memos

  - Send hard copy and link to electronic copy of each tech memo to OLE sections

- NEPA/404 merge concurrence point 3 (alternatives carried forward)

  - OLE NEPA presents quick review of P&N (primary projects)

- Preliminary DEIS and draft 4(f) for NEPA review ONLY.  Document may not be complete.  Return for revisions

- DEIS and draft 4(f) for review by all (OLE sections, Design, and Bridge, if project includes major bridge) – return for revisions

  - Include cooperating agencies in review

- DEIS and draft 4(f) for FHWA review – return for revisions

  - Mark date given to FHWA  (3week review period)

- DEIS and draft 4(f) for FHWA and IA DOT signature.  For local systems projects, joint lead agencies sign.

- Distribution of signed DEIS and draft 4(f)

  - EPA publishes notice of availability (NOA) in Federal Register

  - Consultant drafts NOA and/or cover letter on DOT letterhead for OLE NEPA approval.

  - Consultant provides OLE NEPA copy of signed NOA and/or cover letter and list of recipients.  (Agency Coordination distribution list)

- Public Hearing

  - 15 days following distribution of DEIS

  - OLE Hearing Section will place NOA in local papers

  - Provide public formal transcript of hearing

- Comment period for DEIS and public hearing is 45 days from date of the NOA

- Evaluate and respond to substantive comments (District/OLE/consultant usually addresses comments)

- NEPA/404 merge concurrence point 4 (Preferred Alternative)

  - Wetlands Section is lead (primary projects)

  - Usually a mailing instead of a meeting

- Obtain written FHWA concurrence on type of FEIS to be produced (traditional, condensed, abbreviated – see FHWA TA T6640.8A VI.A through C)

- Prepare FEIS and final 4(f)

- Preliminary FEIS and final 4(f) for NEPA review ONLY – return for revisions

- FEIS and final 4(f) for review by all (OLE sections, Design, and Bridge, if project includes major bridge) – return for revisions

- FEIS and final 4(f) for FHWA review – return for revisions

  - FHWA will include legal sufficiency review (3 week review period)

- FEIS and final 4(f) for FHWA and IA DOT signature.  For local systems projects, joint lead agencies sign.

- Distribution of signed FEIS and final 4(f)

  - EPA publishes the NOA in Federal Register

  - Consultant drafts the NOA and/or cover letter on DOT letterhead for OLE NEPA approval.

  - Consultant provides OLE NEPA copy of signed NOA and/or cover letter and list of recipients.  (EIS distribution list)

- Evaluate and respond to substantive comments (waiting period)

- Prepare ROD for review (no sooner than 30 days after NOA in Federal Register or 90 days after NOA for DEIS) – return for revisions

- FHWA signs ROD

- Distribute ROD